## Sheet1
Sprint | # | User Story | Prerequisites | Expected Results | Actual Results | Date Tested | Tester | Actions Taken
1 | 1 | As a user, I want to be able to login to the application using a unique username and password. | None | Application runs and in the Login Screen after inserting a valid username-password pair the main application window appears | As expected | 2020-03-06 | Chrysis | None
| 2 | As a user, I want to be able to view all invoices | 1 | Application runs and after selecting 'Invoice' in the side menu and 'View All' in the top bar menu you can see all the invoices from the Database, in a grid. You can also filter results by Date and Customer name. | As expected | 2020-03-06 | Chrysis | None
| 3 | As a user, I want to view an Invoice's details | 1 , 2 | Application runs and after selecting 'Invoice' in the side menu and 'View' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details including customer information and products are displayed in their corresponding elements. | As expected | 2020-03-06 | Chrysis | None
| 4 | As a user, I want to be able to create invoices | 1 | Application runs and after selecting 'Invoice' in the side menu and 'Create' in the top bar menu you can select the Customer, adjust his info, select Products, adjust their prices/quantity and by pressing Complete send the information to the Database. | No validations in Quantity and Price for negative values | 2020-03-07 | Chrysis | Awaiting Fix
| 5 | As a user, I want to be able to edit an invoice | 1, 4
| 6 | As a user, I want to be able to print invoices | 1, 4
| 7 | As a user, I want to be able to export invoices as pdf | 1, 4
| 8 | As a user, I want to be able to preview the invoice before printing/exporting | 1, 4
| 9 | As a user, I want to be able to view existing customers | 1
| 10 | As a user, I want to be able to register a new customer | 1
| 11 | As a user, I want to be able to edit a customer | 1, 10
| 12 | As an admin, I want to be able to remove a customer | 1, 9, 11
| 13 | As a user, I want to be able to create a new product | 1
| 14 | As a user, I want to be able to view all products | 1
| 15 | As a user, I want to be able to update the stock of an existing product | 1, 13
| 16 | As a user, I want to be able to modify an existing product | 1, 13
| 17 | As an admin, I want to be able to add or remove user accounts to the application. | 1