## Sheet1
Sprint | # | User Story | Prerequisites | Expected Results | Actual Results | Date Tested | Tester | Actions Taken
1 | 1 | As a user, I want to be able to login to the application using a unique username and password. | None | Application runs and in the Login Screen after inserting a valid username-password pair the main application window appears | As expected | 2020-03-06 | Chrysis | None
| 2 | As a user, I want to be able to view all invoices | 1 | Application runs and after selecting 'Invoice' in the side menu and 'View All' in the top bar menu you can see all the invoices from the Database, in a grid. You can also filter results by Date and Customer name. | As expected | 2020-03-06 | Chrysis | None
| 3 | As a user, I want to view an Invoice's details | 1 , 2 | Application runs and after selecting 'Invoice' in the side menu and 'View' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details including customer information and products are displayed in their corresponding elements. | As expected | 2020-03-06 | Chrysis | None
| 4 | As a user, I want to be able to create invoices | 1 | Application runs and after selecting 'Invoice' in the side menu and 'Create' in the top bar menu you can select the Customer, adjust his info, select Products, adjust their prices/quantity and by pressing Complete send the information to the Database. | No check in Quantity and Price for negative values Duplicate products should not be allowed | 2020-03-07 | Chrysis | Awaiting Fix
| 5 | As a user, I want to be able to edit an invoice | 1, 4 | Application runs and after selecting 'Invoice' in the side menu and 'Edit' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details including customer information and products are displayed in their corresponding elements and then you can edit the products information. | No check in Quantity and Price for negative values Duplicate products should not be allowed When an invoice is already loaded, pressing load again will not clear previous invoice | 2020-03-08 | Chrysis | Awaiting Fix (Fixed loading new invocie)
| 6 | As a user, I want to be able to print invoices | 1, 3 | Application runs and after selecting 'Invoice' in the side menu and 'View' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details are loaded and when you press print then Adobe Acrobat Reader runs with the print dialog window open | No check if an invoice is loaded or not. The temp pdf is not removed afterwards | 2020-03-08 | Chrysis | Awaiting Fix
| 7 | As a user, I want to be able to export invoices as pdf | 1, 3 | Application runs and after selecting 'Invoice' in the side menu and 'View' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details are loaded and when you press save then the invoice is saved in the predetermined location. | No check if an invoice is loaded or not. | 2020-03-08 | Chrysis | Awaiting Fix
| 8 | As a user, I want to be able to preview the invoice before printing/exporting | 1, 3 | Application runs and after selecting 'Invoice' in the side menu and 'View' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details are loaded and when you press preview then Adobe Acrobat Reader and displays the pdf to be created. | No check if an invoice is loaded or not. The temp pdf is not removed afterwards | 2020-03-08 | Chrysis | Awaiting Fix
| 9 | As a user, I want to be able to view existing customers | 1 | Application runs and after selecting 'Customers' in the side menu and 'View' in the top bar menu you can see all the customers from the Database, in a grid. You can also filter results by Balance, Customer name and City. | As expected | 2020-03-08 | Chrysis | None
| 10 | As a user, I want to be able to register a new customer | 1 | Application runs and after selecting 'Customers' in the side menu and 'Create' in the top bar menu you can add all the information you need to create a new customer and then press Create to complete. | No email and phone number validations | 2020-03-08 | Chrysis | Awaiting Fix
| 11 | As a user, I want to be able to edit a customer | 1, 10 | Application runs and after selecting 'Customers' in the side menu and 'Edit' in the top bar menu and load the customer you want you can edit all his information then press Update to complete. | No email and phone number validations | 2020-03-08 | Chrysis | Awaiting Fix
| 12 | As an admin, I want to be able to remove a customer | 1, 9, 11 | Application runs and after selecting 'Customers' in the side menu and View in the top bar menu you can see all the customers from the Database, in a grid and by selecting Delete from the options on the right the customer is removed. | Cannot remove customers that are referenced in the Database as that violated the foreign keys constraints | 2020-03-08 | Chrysis | Awaiting Fix
| 13 | As a user, I want to be able to create a new product | 1 | Application runs and after selecting 'Product' in the side menu and Create in the top bar menu you can add all the information of a product in the textboxes and then complete with the Create button. | No check in most text boxes for negative values (price, cost, stock) | 2020-03-08 | Chrysis | Awaiting Fix
| 14 | As a user, I want to be able to view all products | 1 | Application runs and after selecting 'Product' in the side menu and 'View' in the top bar menu you can see all the products from the Database, in a grid. You can also filter results by Category, Product name and Status. | As expected | 2020-03-08 | Chrysis | None
| 15 | As a user, I want to be able to update the stock of an existing product | 1, 13 | Application runs and after selecting 'Product' in the side menu and 'Edit' in the top bar menu and load the product you want you can edit all its information then press Update to complete. | No check in most text boxes for negative values (price, cost, stock) No validation for VAT | 2020-03-08 | Chrysis | Awaiting Fix
| 16 | As a user, I want to be able to modify an existing product | 1, 13 | Application runs and after selecting 'Product' in the side menu and 'Edit' in the top bar menu and load the product you want you can edit all its information then press Update to complete. | No check in most text boxes for negative values (price, cost, stock) No validation for VAT | 2020-03-08 | Chrysis | Awaiting Fix
| 17 | As an admin, I want to be able to add or remove user accounts to the application. | 1 | Application runs and after selecting 'Settings' in the side menu you can load all the users/ remove users and add new users | As expected (but its ugly) | 2020-03-08 | Chrysis | Awaiting Beautyfication