## Sheet1
Sprint | # | User Story | Prerequisites | Expected Results | Actual Results | Date Tested | Tester | Actions Taken
1 | 1 | As a user, I want to be able to login to the application using a unique username and password. | None | Application runs and in the Login Screen after inserting a valid username-password pair the main application window appears | As expected | 2020-03-06 | Chrysis | None
| 2 | As a user, I want to be able to view all invoices | 1 | Application runs and after selecting 'Invoice' in the side menu and 'View All' in the top bar menu you can see all the invoices from the Database, in a grid. You can also filter results by Date and Customer name. | As expected | 2020-03-06 | Chrysis | None
| 3 | As a user, I want to view an Invoice's details | 1 , 2 | Application runs and after selecting 'Invoice' in the side menu and 'View' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details including customer information and products are displayed in their corresponding elements. | As expected | 2020-03-06 | Chrysis | None
| 4 | As a user, I want to be able to create invoices | 1 | Application runs and after selecting 'Invoice' in the side menu and 'Create' in the top bar menu you can select the Customer, adjust his info, select Products, adjust their prices/quantity and by pressing Complete send the information to the Database. | No check in Quantity and Price for negative values Duplicate products should not be allowed | 2020-03-07 | Chrysis | Fixed
| 5 | As a user, I want to be able to edit an invoice | 1, 4 | Application runs and after selecting 'Invoice' in the side menu and 'Edit' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details including customer information and products are displayed in their corresponding elements and then you can edit the products information. | No check in Quantity and Price for negative values Duplicate products should not be allowed When an invoice is already loaded, pressing load again will not clear previous invoice | 2020-03-08 | Chrysis | Fixed
| 6 | As a user, I want to be able to print invoices | 1, 3 | Application runs and after selecting 'Invoice' in the side menu and 'View' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details are loaded and when you press print then Adobe Acrobat Reader runs with the print dialog window open | No check if an invoice is loaded or not. The temp pdf is not removed afterwards | 2020-03-08 | Chrysis | Fixed
| 7 | As a user, I want to be able to export invoices as pdf | 1, 3 | Application runs and after selecting 'Invoice' in the side menu and 'View' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details are loaded and when you press save then the invoice is saved in the predetermined location. | No check if an invoice is loaded or not. | 2020-03-08 | Chrysis | Fixed
| 8 | As a user, I want to be able to preview the invoice before printing/exporting | 1, 3 | Application runs and after selecting 'Invoice' in the side menu and 'View' in the top bar menu and then insert the Invoice ID in the corresponding text box, all the invoice's details are loaded and when you press preview then Adobe Acrobat Reader and displays the pdf to be created. | No check if an invoice is loaded or not. The temp pdf is not removed afterwards | 2020-03-08 | Chrysis | Fixed
| 9 | As a user, I want to be able to view existing customers | 1 | Application runs and after selecting 'Customers' in the side menu and 'View' in the top bar menu you can see all the customers from the Database, in a grid. You can also filter results by Balance, Customer name and City. | As expected | 2020-03-08 | Chrysis | None
| 10 | As a user, I want to be able to register a new customer | 1 | Application runs and after selecting 'Customers' in the side menu and 'Create' in the top bar menu you can add all the information you need to create a new customer and then press Create to complete. | As expected | 2020-03-08 | Chrysis | None
| 11 | As a user, I want to be able to edit a customer | 1, 10 | Application runs and after selecting 'Customers' in the side menu and 'Edit' in the top bar menu and load the customer you want you can edit all his information then press Update to complete. | As expected | 2020-03-08 | Chrysis | None
| 12 | As an admin, I want to be able to remove a customer | 1, 9, 11 | Application runs and after selecting 'Customers' in the side menu and View in the top bar menu you can see all the customers from the Database, in a grid and by selecting Delete from the options on the right the customer is removed. | Cannot remove customers that are referenced in the Database as that violated the foreign keys constraints | 2020-03-08 | Chrysis | Fixed
| 13 | As a user, I want to be able to create a new product | 1 | Application runs and after selecting 'Product' in the side menu and Create in the top bar menu you can add all the information of a product in the textboxes and then complete with the Create button. | No check in most text boxes for negative values (price, cost, stock) | 2020-03-08 | Chrysis | Fixed
| 14 | As a user, I want to be able to view all products | 1 | Application runs and after selecting 'Product' in the side menu and 'View' in the top bar menu you can see all the products from the Database, in a grid. You can also filter results by Category, Product name and Status. | As expected | 2020-03-08 | Chrysis | None
| 15 | As a user, I want to be able to update the stock of an existing product | 1, 13 | Application runs and after selecting 'Product' in the side menu and 'Edit' in the top bar menu and load the product you want you can edit all its information then press Update to complete. | No check in most text boxes for negative values (price, cost, stock) No validation for VAT | 2020-03-08 | Chrysis | Fixed
| 16 | As a user, I want to be able to modify an existing product | 1, 13 | Application runs and after selecting 'Product' in the side menu and 'Edit' in the top bar menu and load the product you want you can edit all its information then press Update to complete. | No check in most text boxes for negative values (price, cost, stock) No validation for VAT | 2020-03-08 | Chrysis | Fixed
| 17 | As an admin, I want to be able to add or remove user accounts to the application. | 1 | Application runs and after selecting 'Settings' in the side menu you can load all the users/ remove users and add new users | As expected (but its ugly) | 2020-03-08 | Chrysis | Fixed
Sprint | # | User Story | Prerequisites | Expected Results | Actual Results | Date Tested | Tester | Actions Taken
2 | 18 | As a user, I want to be able to view the receipts | 1 | Application runs and after selecting 'Receipt' in the side menu and 'View All' in the top bar menu you can see all the receipts from the Database, in a grid. You can also filter results by Date and Customer name. | As expected | 2020-04-18 | Chrysis | None
| 19 | As a user, I want to be able to create receipts | 1 | Application runs and after selecting 'Receipt' in the side menu and 'Create' in the top bar menu you can select the Customer, add payments and by pressing Complete send the information to the Database. | As expected | 2020-04-18 | Chrysis | None
| 20 | As a user, I want to be able to edit a receipt | 1, 19 | Application runs and after selecting 'Receipt' in the side menu and 'Edit' in the top bar menu and then insert the Receipt ID in the corresponding text box, all the receipt's details including customer information and payments are displayed in their corresponding elements and then you can edit the payments information. | No check for leaving payments empty | 2020-04-18 | Chrysis | Fixed, doesn’t update with no payments and also alerts the user
| 21 | As an admin, I want to be able to delete a receipt | 1, 18, 20 | Application runs and after selecting 'Receipt' in the side menu and View All in the top bar menu you can see all the receipts from the Database, in a grid and by selecting Delete from the options on the right the receipt is removed. | As expected | 2020-04-18 | Chrysis | None
| 22 | As an admin, I want to be able to view all orders | 1 | Application runs and after selecting 'Order' in the side menu and 'View All' in the top bar menu you can see all the orders from the Database, in a grid. You can also filter results by Date, Customer name, status and city. | As expected | 2020-04-18 | Chrysis | None
| 23 | As a user, I want to be able to mark an order as ready/not ready | 1, 22 | Application runs and after selecting 'Order' in the side menu and View All in the top bar menu you can see all the orders from the Database, in a grid and by selecting Mark as Ready/Not ready from the options on the right the order is updated. | As expected | 2020-04-18 | Chrysis | None
| 24 | As a user, I want to be able to issue an order as invoice | 1, 22, 23 | Application runs and after selecting 'Order' in the side menu and View All in the top bar menu you can see all the orders from the Database, in a grid and by selecting Issue as invoice from the options on the right the order is loaded in Create Invoice to be completed. | Works but does not update order status as completed | 2020-04-18 | Chrysis | Fixed, Order status is now properly updated
| 25 | As a user, I want to be able to create orders | 1 | Application runs and after selecting 'Order' in the side menu and 'Create' in the top bar menu you can select the Customer, select Products, adjust their prices/quantity and by pressing Complete send the information to the Database. | As expected | 2020-04-18 | Chrysis | None
| 26 | As a user, I want to be able to edit an order | 1, 25 | Application runs and after selecting 'Order' in the side menu and 'Edit' in the top bar menu and then insert the Order ID in the corresponding text box, all the order's details including customer information and products are displayed in their corresponding elements and then you can edit the products information. | As expected | 2020-04-18 | Chrysis | None
| 27 | As an admin, I want to be able to delete an order | 1, 22, 26 | Application runs and after selecting 'Order' in the side menu and View All in the top bar menu you can see all the orders from the Database, in a grid and by selecting Delete from the options on the right the order is removed. | As expected | 2020-04-19 | Chrysis | None
| 28 | As a user, I want to be able to view an offer | 1 | Application runs and after selecting 'Offer' in the side menu and View All in the top bar menu you can see all the offers from the Database, in a grid. You can also filter results by Date, Customer name, status and city. | As expected | 2020-04-19 | Chrysis | None
| 29 | As a user, I want to be able to create an offer | 1 | Application runs and after selecting 'Offer' in the side menu and 'Create' in the top bar menu you can select the Customer, select Products, adjust their offer price and by pressing Complete send the information to the Database. | No check for offer price to being larger than actual price also no confirmation on success of create | 2020-04-19 | Chrysis | Fixed
| 30 | As a user, I want to be able to edit an offer | 1, 29 | Application runs and after selecting 'Offer' in the side menu and 'Edit' in the top bar menu and then insert the Offer ID in the corresponding text box, all the offer's details including customer information and products are displayed in their corresponding elements and then you can edit the products information. | Cant edit from view all, also no confirmation on success of edit | 2020-04-19 | Chrysis | Fixed
| 31 | As an admin, I want to be able to delete an offer | 1, 28, 30 | Application runs and after selecting 'Offer' in the side menu and View All in the top bar menu you can see all the offers from the Database, in a grid and by selecting Delete from the options on the right the offer is removed. | As expected | 2020-04-19 | Chrysis | None
| 32 | As a user, I want to be able to view all expenses | 1 | Application runs and after selecting 'Expenses' in the side menu and 'View All' in the top bar menu you can see all the expenses from the Database, in a grid. You can also filter results by Date, Company status and category. | As expected | 2020-04-19 | Chrysis | None
| 33 | As a user, I want to be able to view an expense | 1, 32 | Application runs and after selecting 'Expenses' in the side menu and View in the top bar menu and then insert the Expense ID in the corresponding text box, all the expense's details including are displayed in their corresponding elements | As expected | 2020-04-19 | Chrysis | None
| 34 | As a user, I want to be able to view the credit notes | 1 | Application runs and after selecting 'Credit Note' in the side menu and View All in the top bar menu you can see all the credit notes from the Database, in a grid. You can also filter results by Date and Customer name. | As expected | 2020-04-19 | Chrysis | None
| 35 | As an admin, I want to be able to delete a credit note | 1, 34 | Application runs and after selecting ''Credit Note' in the side menu and View All in the top bar menu you can see all the credit notes from the Database, in a grid and by selecting Delete from the options on the right the credit note is removed. | As expected | 2020-04-19 | Chrysis | None
Sprint | # | User Story | Prerequisites | Expected Results | Actual Results | Date Tested | Tester | Actions Taken
3 | 36 | As a user, I want to be able to create credit notes | 1 | Application runs and after selecting 'Credit Note' in the side menu and 'Create' in the top bar menu you can select the Customer, select Products, adjust their prices/quantity and by pressing Complete send the information to the Database. | Not properly clearing all fields when completing a credit note | 2020-05-02 | Chrysis | Fixed
| 37 | As a user, I want to be able to edit a credit note | 1, 36 | Application runs and after selecting 'Credit Note' in the side menu and 'Edit' in the top bar menu and then insert the credit note ID in the corresponding text box, all the it's details including customer information and products are displayed in their corresponding elements and then you can edit the products information. | Not properly clearing all fields when edititng a credit note | 2020-05-02 | Chrysis | Fixed
| 38 | As a user, I want to be able to add an expense | 1 | Application runs and after selecting 'Expenses' in the side menu and 'Create' in the top bar menu you can select the Customer, select Products, adjust their prices/quantity and by pressing Complete send the information to the Database. | Wrong | 2020-05-02 | Chrysis | Fixed
| 39 | As a user, I want to be able to edit an expense | 1, 38 | Application runs and after selecting 'Expenses' in the side menu and 'Edit' in the top bar menu and then insert the expense ID in the corresponding text box, all the it's details displayed in their corresponding elements and then you can edit. | Wrong | 2020-05-02 | Chrysis | Fixed
| 40 | As a user, I want to be able to delete an expense | 1, 32 | Application runs and after selecting 'Expenses' in the side menu and View All in the top bar menu you can see all the expenses from the Database, in a grid and by selecting Delete from the options on the right the expense is removed. | As expected | 2020-05-02 | Chrysis | None
| 41 | As an admin, I want to be able to export all data as CSV | 1 | Application runs and after selecting 'Settings' in the side menu and then Database in the top bar menu you can select path to export the DB as SQL script. | As expected | 2020-05-02 | Chrysis | None
| 42 | As an admin, I want to be able to export/backup the database | 1 | Application runs and after selecting 'Settings' in the side menu and then Database in the top bar menu you can select path to export the DB as CSV file. | As expected | 2020-05-02 | Chrysis | None
| 43 | As a user, I want to be able to preview the credit note before printing/exporting | 1, 34 | Application runs and after selecting 'Credit Note' in the side menu and 'View' in the top bar menu and then insert the credit note ID in the corresponding text box, all the it's details are loaded and when you press preview then Adobe Acrobat Reader runs and displays the pdf to be created. | As expected | 2020-05-02 | Chrysis | None
| 44 | As a user, I want to be able to export a credit note to pdf | 1, 34 | Application runs and after selecting 'Credit Note' in the side menu and 'View' in the top bar menu and then insert the credit note ID in the corresponding text box, all the it's details are loaded and when you press save then the it is saved in the predetermined location. | As expected | 2020-05-02 | Chrysis | None
| 45 | As a user, I want to be able to print credit notes | 1, 34 | Application runs and after selecting 'Credit Note' in the side menu and 'View' in the top bar menu and then insert the credit note ID in the corresponding text box, all the it's details are loaded and when you press print then Adobe Acrobat Reader runs with the print dialog window open | As expected | 2020-05-02 | Chrysis | None
| 46 | As a user, I want to be able to preview the offer before printing/exporting | 1, 28 | Application runs and after selecting 'Offer' in the side menu and 'View' in the top bar menu and then insert the offer ID in the corresponding text box, all the it's details are loaded and when you press preview then Adobe Acrobat Reader runs and displays the pdf to be created. | As expected | 2020-05-03 | Chrysis | None
| 47 | As a user, I want to be able to export an offer as pdf | 1, 28 | Application runs and after selecting 'Offer' in the side menu and 'View' in the top bar menu and then insert the offer ID in the corresponding text box, all the it's details are loaded and when you press save then the it is saved in the predetermined location. | As expected | 2020-05-03 | Chrysis | None
| 48 | As a user, I want to be able to print an offer | 1, 28 | Application runs and after selecting 'Offer' in the side menu and 'View' in the top bar menu and then insert the offer ID in the corresponding text box, all the it's details are loaded and when you press print then Adobe Acrobat Reader runs with the print dialog window open | As expected | 2020-05-03 | Chrysis | None
| 49 | As a user, I want to be able to preview the order before printing/exporting | 1, 22 | Application runs and after selecting 'Order' in the side menu and 'View' in the top bar menu and then insert the order ID in the corresponding text box, all the it's details are loaded and when you press preview then Adobe Acrobat Reader runs and displays the pdf to be created. | Decimals | 2020-05-03 | Chrysis | Fixed
| 50 | As a user, I want to be able to export an order as pdf | 1, 22 | Application runs and after selecting 'Order' in the side menu and 'View' in the top bar menu and then insert the order ID in the corresponding text box, all the it's details are loaded and when you press save then the it is saved in the predetermined location. | Decimals | 2020-05-03 | Chrysis | Fixed
| 51 | As a user, I want to be able to print an order | 1, 22 | Application runs and after selecting 'Order' in the side menu and 'View' in the top bar menu and then insert the order ID in the corresponding text box, all the it's details are loaded and when you press print then Adobe Acrobat Reader runs with the print dialog window open | Decimals | 2020-05-03 | Chrysis | Fixed
| 52 | As a user, I want to be able to preview the receipt before printing/exporting | 1, 18 | Application runs and after selecting 'Receipt' in the side menu and 'View' in the top bar menu and then insert the receipt ID in the corresponding text box, all the it's details are loaded and when you press preview then Adobe Acrobat Reader runs and displays the pdf to be created. | As expected | 2020-05-03 | Chrysis | None
| 53 | As a user, I want to be able to export receipts as pdf | 1, 18 | Application runs and after selecting 'Receipt' in the side menu and 'View' in the top bar menu and then insert the receipt ID in the corresponding text box, all the it's details are loaded and when you press save then the it is saved in the predetermined location. | As expected | 2020-05-03 | Chrysis | None
| 54 | As a user, I want to be able to print receipts | 1, 18 | Application runs and after selecting 'Receipt' in the side menu and 'View' in the top bar menu and then insert the receipt ID in the corresponding text box, all the it's details are loaded and when you press print then Adobe Acrobat Reader runs with the print dialog window open | As expected | 2020-05-03 | Chrysis | None
| 55 | As a user, I want to be able to create a statement for a customer | 1, 2, 18, 34 | Application runs and after selecting 'Statement' in the side menu and 'Create' in the top bar menu you can select the customer and the date range to retrieve all invoices, credit notes and receipts matching the dates. | As expected | 2020-05-03 | Chrysis | None
| 56 | As a user, I want to be able to preview the statement before printing/exporting | 1, 55 | Application runs and after selecting 'Statement' in the side menu and 'Create' in the top bar menu and after you create a statement you press preview then Adobe Acrobat Reader runs and displays the pdf to be created. | As expected | 2020-05-03 | Chrysis | None
| 57 | As a user, I want to be able to export a statement as pdf | 1, 55 | Application runs and after selecting 'Statement' in the side menu and 'Create' in the top bar menu and after you create a statement you press save then the it is saved in the predetermined location. | As expected | 2020-05-03 | Chrysis | None
| 58 | As a user, I want to be able to print a statement | 1, 55 | Application runs and after selecting 'Statement' in the side menu and 'Create' in the top bar menu and after you create a statement you press print then Adobe Acrobat Reader runs with the print dialog window open | As expected | 2020-05-03 | Chrysis | None